## Sheet1
Phase III: Status Report
Plan Tasks |  | Completed By: | Week to Complete | Accomplishment | Challenges
Part A: E-R diagram | ADDRESSES |  | Week 1: 11/19/23 - 11/25/23
ORGANIZATION
MANUFACTURER
CTD_GPS
CTD_DATA
CTD_OPERATOR
CTD_EQUIPMENT
CTD_LOG
Part B: Normalization | ADDRESSES
ORGANIZATION
MANUFACTURER
CTD_GPS
CTD_DATA
CTD_OPERATOR
CTD_EQUIPMENT
CTD_LOG
Part C: Revised Relational Schema | ADDRESSES
ORGANIZATION
MANUFACTURER
CTD_GPS
CTD_DATA
CTD_OPERATOR
CTD_EQUIPMENT
CTD_LOG
Part D: Front End Interface | Home Page |  | Week 2: 11/26/23 - 12/02/23
Overview
Project Desription
Members + Contacts
Logo + Team Name
Title
SQL Queries # 1
SQL Queries # 2
SQL Queries # 3
SQL Queries # 4
Part E: Project Documentation and Final Report | Cover Page
Logo + Team Name
Members + Contacts
Final Report
Introduction
Objectives and Scope of the Project
Related or Existing Solutions
Overview of the following:
Architecture or Design Diagrams
ER Diagram
Normalization Proof to BCNF
Relational Schema Diagram
SQL Queries
Web Interface
Conclusions with Contribution
Final Thoughs: Future Works and References
Appendix
Appendix A: ER Diagram
Appendix B: Normalization Proof to BCNF
Appendix C: Relational Schema Diagram
Appendix D: Screenshots of functional SQL Queries
Appendix E: Screenshots of functional Web Interface
Part F: Implementation and Coding
Part G: Prototype | Slide #1 |  | Week 3: 12/03/23 - 12/08/23
Logo + Team Name
Members + Contacts
Slide #2
Overview Include the following:
Objective: Why built this Application
Target Audience: Who will use our Application
Main Feature of Application
Slide #3
ER design: main entities and defend conceptual design
Slide #4
Relational Schema: any major differences between Phase II and Phase III schemas
Slide #5
Normalization Proof: Demonstrate that database is in BCNF, discuss 1 or 2 relations.
Slide #6
Prototype/Demo: Demo exhibiting working functionalities of the front-end.
Slide #7
Conclusion/Challenges: Any challenges and potential future work enhancements.
Video Presentation